## Slide 1: Team Velocity- Sprint 1
Chart: Team Velocity (January 23, 2023 – March 10, 2023)
| Catalyst 1a | Catalyst 1b | Catalyst 1c
Story Points | 71 | 44 | 27
Story Points Completed | 71 | 44 | 26

## Slide 2: Completed/Committed Ratio- Sprint 1
Chart: 
| Completed- Catalyst 1a | Completed- Catalyst 1b | Completed- Catalyst 1c | Incomplete - Catalyst 1
Total Story Points | 71 | 44 | 26 | 1

## Slide 3: Burndown Charts- Sprint 1
Chart: Catalyst 1a (January 23, 2023 - February 6, 2023): Burn Down Chart
| 44949 | 44949 | 44951 | 44951 | 44953 | 44953 | 44958 | 44960 | 44962 | 44962 | 44963 | 44963
Work Scope | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71
Remaining Work | 63 | 61 | 56 | 48 | 43 | 35 | 27 | 19 | 16 | 8 | 3 | 0
Chart: Catalyst 1b (February 6, 2023 - February 20, 2023): Burn Down Chart
| 44963 | 44965 | 44965 | 44967 | 44972 | 44977 | 44977
Work Scope | 44 | 44 | 44 | 44 | 44 | 44 | 44
Remaining Work | 43 | 35 | 27 | 19 | 11 | 8 | 0
Chart: Catalyst 1c (February 20, 2023 - March 10, 2023): Burn Down Chart
| 44980 | 44981 | 44983 | 44990 | 44990 | 44991
Work Scope | 19 | 27 | 27 | 27 | 27 | 27
Remaining Work | 16 | 24 | 16 | 11 | 6 | 1

## Slide 4: Team Velocity- Sprint 2
Chart: Sprint 2 Velocity
| Sprint 2
Story Points | 85
Story Points Completed | 84

## Slide 5: Completed/Committed Ratio- Sprint 2
Chart: 
| Completed- Catalyst 2 | Incomplete - Catalyst 2
Total Story Points | 84 | 1

## Slide 6: Burndown Chart- Sprint 2
Chart: Catalyst 2: Burn Down Chart
| 45007 | 45009 | 45010 | 45012 | 45026 | 45030 | 45033 | 45036 | 45037 | 45041 | 45043
Work Scope | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
Remaining Work | 85 | 80 | 78 | 73 | 68 | 55 | 50 | 25 | 24 | 12 | 1
Chart: Catalyst 2: Burn Up Report
| 45009 | 45010 | 45012 | 45026 | 45030 | 45033 | 45036 | 45037 | 45041 | 45043
Completed Work | 13 | 15 | 20 | 25 | 38 | 43 | 68 | 69 | 81 | 84
Work Scope | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85